VDM & WOW State Of the World Sept 25th MattFe

Schedule Notes

o	Schedule arranged to do Win 3.1 Merge last since Win 3.1 APIs are changing and we could go into Beta with Win 3.0 APIs.

o 	Does NOT include Win 3.1 Multi Media, or other extensions being planned for Win 3.1

o	Does NOT include Toolhelp APIs.

o	Additional USER items were added when JeffPar left - as a part of the handover

Have Run in the past (some features don't work)

Old: Hello.EXE,  Generic.EXE,  Reversi.EXE,  Calendar.EXE, Notepad.EXE, Clock.EXE, Minesweaper, calculator, tetris, WinWord, AmiPro, Corel Draw, Write

Corel prints, Solitair

386 - 16-bit Protect Mode - stable in public build

WOW and DOSem run with Insignia CCPU

MIPS Threader is running well on DEC Station

Immediate Project Goals

Get WinWord Running in the public build in protect mode

Recruit JeffPar replacement

Develop SCS

Integration of Insignia Threader + WOW and DOSEM

First Delivery of High Quality Threader from Insignia

User

WOW - runs on 386/486 using v86 mode and Mips with Insignia CCPU

Jeff left the group, currently no more progress is being made on WOW user

GDI

Agreement reached with Win32 on Device Dependent Bit Maps support

Chandan is focused on Clipboard Implementation

Kernel

16-Bit Protect mode is now running well

improve protect mode fileio performance

multi tasking

Matt's focus is on integration with Insignia and recruiting a jeffpar replacement

DOS Emulation

Thereses & AndreV has progressed the h/w desktop and console graphics, work now needs to be done by insignia

WOW runs well on DOSem

Hard Error design understood and requirements given to jima, spec updated

SCS Design DOC written and reviewed

SCS Development started

Support added to start DOS binary from NT command line

Sudeep is focused on closing out the Single Command Shell (SCS)

(386/486)

DOSem works well on NT in v86 mode

WOW runs well  v86 and protect mode

Support added to start WOW tasks directly from program manager

Dave is now focused on the x86 IEU

Clipboard - Spec Complete, dev started

DDE	- Spec Complete, new design work needs to be done for changes in Win32 DDE

OLE	- Spec Complete,  new design work needs to be done for changes in Win32 DDE

Insignia

Insignia were here for 2 weeks and completed most integration work with DOSEM and WOW

We had integration problems porting the threader to MIPS with problems

The MIPS threader on the DEC station runs trapper tests and is thought now to be as stable as Generic 3.0.

MIPS delta 2 tests are now running (all static tests run)

Generic Delta 2 runs Windows 3.0, Lotus 1-2-3, dBase IV, Word Perfect

Generic 3.0 - they are now fixing more bugs than are being raised

I expect to have the High Quality threader running on Jazz by the end of Sept.

Printing

CorelDrw prints

DPMI 0.9

DPMI .9 Enough to support Windows is functional (more work is required to become fully .9 compliant).

Net Support

NetBIOS and WinNet Api's work handed over to Net group (RFrith)

Named Pipes - will be done as a part DOS Emulation

XMS

Complete and running using DOS HiMem sources, DOSem now loads high, on MIPS and x86

No Design Work Done Yet

Win 3.1 plan to include Multi-Media api in the base - we'll need wow support

Generic h/w needs to be planned, design work needs to be done to keep NT robust.

Risks

JeffPar leaving the group will cause about a 3 month slip.    I am actively trying to recruit a replacement.