## Slide 1
OS/2 on Windows/NT
Yaron Shamir
Notes: Drawing shadowed boxes with PowerPoint is easy. Simply use the Rectangle tool to draw the box and then choose Shadowed from the Draw menu.
Be sure to delete this word processing box before using this template for your own presentation.

## Slide 2
FY '92 Objectives
g 1. Must: Run OS/2 1.X Server applications* binary compatible on NT Product 1: - SQL server
- Mail server
- Macintosh server (investigate AFP stack)
- Other server apps: Comm (investigate DLC support), Notes, Saros).
* Potentially modify install programs.

## Slide 3
FY '92 Objectives (cont)
g 2. Goal: Run server apps' utility programs binary compatible:
E.G.
- Install programs.
- Config/Maintenace front-ends a-la LM admin UI.

## Slide 4
FY '92 Objectives (cont)
g 3. Try: Full non-PM OS2 1.X functionality (All of VIO/KBD/MOU/MON).
This will allow apps like Word 5.5, Rbase, PWB to run binary compatible.

## Slide 5
FY '92 Objectives (cont)
g Detailed design for PM:
- Design point as described in earlier presentation.
- Write a detailed internal specification and prototype split screen groups. As PM requirements get clearer, adjust manpower to build product.

## Slide 6
Status of Implementation
g Started implementation April 1991. Designed and impemented APIs, thunk layer, loader and kernel support to a level that allows us to fully build our SW self hosted (OS2 1.X compiler, linker etc. work binary compatible on OS2/NT).
g ~130 APIs implemented. ~10 left to complete SQL server list.
g Group included LarryS and YaronS. AviN joined this week.

## Slide 7
Milestones for Product 1
g Run SQL server Q3 1991.
g Spec Kernel support neded for product 1 by July 15th. Discuss with Davec to mutually commit.
g Integrate OS2 into NT console by Oct 15 (currently using kdb COM1 for UI).
g Code complete Dec 1st.
g System Test Jan 31st.

## Slide 8
Staffing Plan for FY'92
T Total Head Count - 10 SDE + 1 admin.
Split by function:
g OS2 server apps support - 5 (3).
g OS/2 VIO support - 3 (0).
g PM design and prototype - 2 (0).
Split by Location:
9 at Haifa, 1 at Redmond. Plan for integration trips.

## Slide 9
Staffing Status
g Recruiting trip June 20. Have 9 SDEs we like and three admins. Will offer to: - Beni Lavi; D12, currently with Intel Haifa. Did their Wizard i860 kernel. - Eli Grushko; D11/12, currently with Ready Systems. Designed and implemented Vertex/Sparc. - Michael Jarus; D12, HW/SW lead for PC to IBM terminal emulation, DOS/X86 experience.
g Next growth (h.c. max 10) December.

## Slide 10
Logistics
g Have a place next-door to Intel Haifa. Lease for 1 year with extension option. Got a local project mgr to refit the space for out needs.
g Working with Intel on a low-cost high-speed network solution for SLM.
g Working with MIS and intenational F&A on legal, accouting, HR issues. Will use Intel as our model.
g Plan to 'open the doors' for SDEs in Haifa October 1991.