# Monthly Milestones

## November - Functional Top Level Windows

### Client/server tool generates working 386 code

### Core Window manager working, non-preemptive

### Input system scaffolding working

### Top level window user interface working

### Main menus working

### Menu resource loading working

## December - Functional USER32 development platform

### Client/server tool generates working R4000 code

### Client/server stubs completed

### Some dialog controls working

### Start regular mips compiles

## January - Serialization, security, run / debug on Jazz hardware

### Start serialization effort

### Start security effort

### Recheck parameter validation

### Continue mips compiles

## Feburary - Continue core work.

### Continue serialization and security effort

### Complete US keyboard layout support

### Dialog, dialog control & misc UI code ready for test

### Continue mips compiles

## March - Run on Jazz, complete windowed self hosting support

### Receive mips GDI & jazz display driver. Run / debug USER on Jazz hardware

### Complete serialization effort

### Security functionality ready for test

### Window manager ready for test

### Input system ready for test

### Start Unicode effort

## April - Stabilize self hosting support, complete SDK content

### Continue stabilization of self-hosting support

### 'window hooks' ready for test

### clipboard support ready for test

### MDI support ready for test

### Shutdown support ready for test

### Hung app support ready for test

### Hard error user interface ready for test

### Run / debug on Jazz hardware

## May - Deploy self-hosting platform, SDK stabilize month

### May 27th - deploy windowed self-hosting platform for x86, mips.

## June - SDK stabilize month

### Test / bug fix

### Snapshot USER sources for SDK

## July - International support, Unicode support, Win 3.1 integration

### Unicode apis ready for test

### Create international keyboard layout tables

### Create international string sorting tables

### Create international case mapping tables

### Win3.1 feature integration

## August - Last implementation month

### Full international support ready for test

### Win3.1 feature integration

### Test / bug fix

## September

## October

## November

## December

### Test / bug fix