## Slide 1
Internet Server Review
August 16, 1995

## Slide 2
Agenda
Status/Beta Plan
New ship plan
DRG Event Agenda
Performance and Benchmarking Methodology
Recent Internet Statistics on Servers

## Slide 3
Team Status
Dave Malcolm added to product marketing
Kyle Geiger added to program management: will initially focus on performance, ODBC issues, and planning for future ODBC releases
One new development req for setup/admin lead

## Slide 4
Beta Status
On schedule to ship next week (1 week late)
Integrated Publishing and Access Setup/Admin
Technical testing release
  Small audience 150 US, 2 master kits per Sub
  NOT marketing beta
Targeting
  Known good NT testers
  Solution Providers
  Existing Internet Sites (infoseek, bhs)
  Service Providers
  ISV’s
Bug reports via:
  standard Compuserve forums
  email
  internet.microsoft.com web server
Beta support - 1+ PSS engineers, 1 repo engineer

## Slide 5
Functionality Omitted for Beta
HTTP/ODBC for non-Intel
Windows 3.x+NetWare only client support
Domain Filtering
DNS Admin
MD5 Authentication
SSL
Licensing support

## Slide 6
Status: SSL
SSPI provider in development
  client complete this week
  server complete next week
Web Server integration, 2 weeks dev
Scoping out administration work
X.509 certificate issues need to be worked out
Been “challenged” twice recently

## Slide 7
The Plan
Performance, Reliability, SSL
Pull in Publishing Edition RTM to 12/1/95
  Drop DNS
  Drop minor features (MGET, HTTP 1.1, etc.)
  Add SSL to Publishing Edition
Slip Access Edition RTM to 4/1/96
Move DNS into NTS/SUR

## Slide 8
New Plan Schedule
Publishing Edition
  Beta 1: Aug 22
  Code complete: Sept 22
  Beta 2: Oct 16
  Ripcord Date: Nov 1
  RC: Nov 15
  RTM: Dec 1
Access Edition
  Beta 1: Aug 22
  Beta 2: Oct 16 (bug fixes only)
  Beta 3: Jan 31 (full functionality)
  RC: Mar 15
  RTM: Apr 1

## Slide 9
Feature Tradeoffs Required to make Dec 1
Less time to spend on performance
Impact on Catapult schedule (2/15->4/1)
No Win95 administration
No auto-discovery of servers
No auto-creation of client or administration shares on server
No remote installation
Limited Beta Feedback

## Slide 10
Marketing impact of Dec 1 RTM
Shipping early is GOOD!
But, some tradeoffs:
  Less ISV support in December timeframe
  December release causes January availability
    Explore December Internet availability (Microsoft Company Store
  Core sales tools only, with less field feedback
  Fewer trophy accounts at launch
  December PR tougher

## Slide 11
Risks in the Dec 1 RTM
Limited resource applied to Admin/Setup/Client area (opened a req to offset this)
Win95 and NT dev maintenance (DHCP, WinSock, utilities)
Impact of SUR beta on test
HTTP/ODBC test mileage and non-Intel
SSL
Setup “split” could be painful

## Slide 12
Extreme Tradeoffs to Improve Confidence in 12/1
Drop SSL
Drop HTTP/ODBC
Drop DNS Admin

## Slide 13
Internet ISV Developers Plan
Three one day events
  Client
  Server (Targeting 15-20 server app vendors Sept 18)
  Tools
Developer kits
  Beta has SDK tools for BGI
  Rolled into BackOffice SDK
  Included MSDN Level II

## Slide 14
Internet ISV Server Agenda
NT/BackOffice Overview (60 min)
Gibraltar Disclosure (30 min)
Writing BGI Extensions, w/ example (60min)
Filters (30 min)
Exchange architecture/opportunities?
Writing great NT server apps (60 min)
WinSock Gems (30 min)
STT (30 min)
MSN Meta Services (30 min)
Roundtable

## Slide 15
Performance Benchmarking Methodology
Performance Task Force: KyleG, DougH, MuraliK, SamPa will drive the following:
Industry Benchmark(s): Plan to work with NSTL at minimum to get an acceptable industry benchmark established for Web
Internal Benchmark(s):
  Weekly: Used for internal development and optimizations in key areas
  Infrequent: Used as a measure to checkpoint what we believe the Industry Benchmarks will portray

## Slide 16
Internal Benchmarks (Weekly)
Weekly runs of mixes in the following areas:
  Cached files (mix of 5-6 different filesizes based on catapult log and site analysis)
  SSL performance in mix
  Multiprocessor performance (x86-based)
  Authenticated use (lowest priority)

## Slide 17
Internal Benchmarks (Infrequent)
Interesting mix of server characteristics which are run infrequently (mainly demonstrate OS limitations, expected to be covered in Industry Benchmarks)
  Minimum CGI application
  Minimum BGI application
  Imagemaps
  Non-cached files
  T1 constrained mix
Measured against: NetScape/NT, NetScape/BSDI, NCSA 1.4/BSDI, Process 1.1/NT, O’Reilly/NT, Netra)

## Slide 18
Web Server Distribution (OS)
Source: http://www.nw.com/zone/WWW/www-servers.html

## Slide 19
Web Server Distribution (Product)
Source: http://www.nw.com/zone/WWW/www-servers.html

## Slide 20
Configuration information for Big Sites
Pathfinder (Time/Warner)
  1 million hits per day
  4 Sun Servers with T3 connection
Playboy
  1.4 million hits per day
  unknown hardware
  Netscape Commerce 1.1 on BSDI Unix
  Two T1 lines moving to a T3
YAHOO
  3+ million hits per day (all text, does not include graphics)
  Several SGI Indy servers and Pentium servers running Unix supported by Netscape
  Customer software, HTTP Server, database, and search engine
  T3 connection @ Netscape

## Slide 21
Configuration information for Big Sites
HotWired
  23-30K hits per day (200,000 members)
  SGI hardware (unknown model)
  Custom HTTP server
InfoSeek
  1 million queries per day
  Custom HTTP server and query engine on Sun Solaris
  T3 and T1 connection

## Slide 22
Configuration Info on Big Sites
Sun
  Solaris/NCSA 1.3
Lycos
  NCSA 1.4
SGI
  NetScape Communications
Novell
  NCSA 1.4
Penthouse
  NetScape Commerce