## Slide 1
Internet Server Review
Nov 15, 1995

## Slide 2
Agenda
Gibraltar Project Status
Catapult Status
SSL/PCT status and architecture
Marketing Plans/Status
Vermeer Demo

## Slide 3
Gibraltar Project Status
Beta 2 RTM’ed on Friday, 11/10
Running on www.microsoft.com, www.nba.com (Starwave)

## Slide 4
Remaining Gibraltar 1.0 Work Items
Licensing work
Performance testing/tuning
Service Pack 3 (ReadDirectoryChanges API)
Bugs not fixed for Beta 2
PCT-enabling of Web server
16-bit “automatic” setup (change directory to correct platform)

## Slide 5
Remaining Gibraltar 1.0 Work Items (cont’d)
PIDs in setup
Proper billboards for setup
Documentation completion
Establish QFE process
PSS verification/test plan
Determine ISAPI SDK delivery plans
Cookie and Referrer featurettes?
SSL Setup Wizard?

## Slide 6
Other Remaining Gibraltar Work Items
“Time Bombed” trial release
  Internet download version, work done post-RTM
Resource Kit(s)
Beta Response Management
“Trophy” Accounts
Package up the Perf Benchmark (MiWEB)
  for reveiwers
  for partners
  for download?

## Slide 7
External Deliverables
Perl perf improvements, DLL
  .exe is 60% faster than previous
  .dll is working, but some issues not yet addressed
Sicily
PCT
STT
Blackbird
Indexing (Mediaview?)
Bengal
IExplore ‘95

## Slide 8
Catapult Status
Working on Catapult Beta 2: expected RTM in 1-2 weeks
Shuttle dev team will be ready for this beta, but doc/PSS/test issues remain
Investigating having Haifa team implement “Remotable Winsock” for product 2

## Slide 9
SSL Status
Included in Beta 2
x.509 certificate process in place with Verisign: 100 beta certs
Current config tools are limited: command-line only
Perf testing forthcoming
Marketing working on a public Internet SLL test server
Non-export version?

## Slide 10
PCT Status
2 weeks away from code complete
Not in IExplore 2.0 (Nov release)
No test plan in place
Inclusion in Gib 1.0 means 1+ month slip
Current POR: “PCT-enable” Web server, ship PCT DLL when ready

## Slide 11
SSL/PCT Architecture
Current implementation is slow
  200+ ms/req for session setup, 34 allocs
  Improvements about to be checked in: expect 50% improvement
  RC4 40-bit is ~11 instructions/byte
Certs stored as LSA secrets per IP address
Implemented as an SSPI provider
  Web server calls SECURITY.DLL, it calls SSPISSL.DLL
  PCT provider implemented in same DLL, shares code
  No use of CAPI today, future may use CAPI for some crypto code

## Slide 12
Gibraltar Bug Status
---------------------------------------------------------------
All Internet Information Server Bugs: Priority 1
---------------------------------------------------------------
Week Starting -----Transactions---- | ----Current Status---- Res:New
Monday New Resolved Closed | Active+Resolved = Open Ratio
|
Nov 13-Nov 15 4 5 1 | 17 10 27 1.25
|
Weekly Summary: |
Nov 6 -Nov 12 16 6 9 | 18 6 24 0.38
Oct 30-Nov 5 19 27 30 | 8 9 17 1.42
Oct 23-Oct 29 12 19 13 | 16 12 28 1.58
Oct 16-Oct 22 4 5 5 | 23 6 29 1.25
---------------------------------------------------------------
All Internet Information Server Bugs
---------------------------------------------------------------
Week Starting -----Transactions---- | ----Current Status---- Res:New
Monday New Resolved Closed | Active+Resolved = Open Ratio
|
Nov 13-Nov 15 4 7 1 | 47 15 62 1.75
|
Weekly Summary: |
Nov 6 -Nov 12 25 10 13 | 50 9 59 0.40
Oct 30-Nov 5 22 37 42 | 35 12 47 1.68
Oct 23-Oct 29 20 22 17 | 50 17 67 1.10
Oct 16-Oct 22 5 10 13 | 52 12 64 2.00

## Slide 13
Catapult Bug Status
---------------------------------------------------------------
All Internet Access Server Bugs: Priority 1
---------------------------------------------------------------
Week Starting -----Transactions---- | ----Current Status---- Res:New
Monday New Resolved Closed | Active+Resolved = Open Ratio
|
Nov 13-Nov 15 10 9 0 | 9 11 20 0.90
|
Weekly Summary: |
Nov 6 -Nov 12 4 1 11 | 8 2 10 0.25
Oct 30-Nov 5 16 32 36 | 5 12 17 2.00
Oct 23-Oct 29 18 15 11 | 21 16 37 0.83
Oct 16-Oct 22 12 15 5 | 18 12 30 1.25
---------------------------------------------------------------
All Internet Access Server Bugs
---------------------------------------------------------------
Week Starting -----Transactions---- | ----Current Status---- Res:New
Monday New Resolved Closed | Active+Resolved = Open Ratio
|
Nov 13-Nov 15 14 10 0 | 54 16 70 0.71
|
Weekly Summary: |
Nov 6 -Nov 12 6 1 14 | 50 6 56 0.17
Oct 30-Nov 5 23 39 60 | 45 19 64 1.70
Oct 23-Oct 29 28 20 21 | 61 40 101 0.71
Oct 16-Oct 22 27 24 23 | 53 41 94 0.89

## Slide 14
Shared Component Bug Status
---------------------------------------------------------------
All Client, Client Setup, Admin Bugs: Priority 1
---------------------------------------------------------------
Week Starting -----Transactions---- | ----Current Status---- Res:New
Monday New Resolved Closed | Active+Resolved = Open Ratio
|
Nov 13-Nov 15 9 4 4 | 27 5 32 0.44
|
Weekly Summary: |
Nov 6 -Nov 12 11 11 15 | 22 5 27 1.00
Oct 30-Nov 5 12 20 21 | 22 9 31 1.67
Oct 23-Oct 29 13 11 11 | 30 10 40 0.85
Oct 16-Oct 22 8 13 3 | 28 10 38 1.63
---------------------------------------------------------------
All Client, Client Setup, Admin Bugs
---------------------------------------------------------------
Week Starting -----Transactions---- | ----Current Status---- Res:New
Monday New Resolved Closed | Active+Resolved = Open Ratio
|
Nov 13-Nov 15 18 8 5 | 77 11 88 0.44
|
Weekly Summary: |
Nov 6 -Nov 12 22 16 20 | 67 8 75 0.73
Oct 30-Nov 5 14 27 35 | 61 12 73 1.93
Oct 23-Oct 29 25 13 13 | 74 20 94 0.52
Oct 16-Oct 22 10 23 13 | 62 20 82 2.30

## Slide 15
Key Marketing Events
MIDL October 26
Beta 2 Press Release November 20
Internet Dev. Web Site November 20
Reviewers Tour November16/20
WW Beta CD Distribution December 1
Internet Strategy Day December 7

## Slide 16
Marketing: Trophy Accounts
30 Strategic Sites
  Corps/Gov’t., ISPs, ICPs, Academic, Channel Partners
Deliver
  Hardware, software (Gibraltar & SQL Server), onsite installation & customization

## Slide 17
Trophy Accounts
Build momentum & mindshare
Gain great experience
Develop packaged services, resource kit(s)
Generate field SE and SP expertise/experience
Get in the way of the competition
Build feedback loop for
  Experience
  Future product requirements

## Slide 18
Trophy Accounts
Resources Defined
  Segal/Needham
  MCS
    Developing proposal
  OEM Partner (DEC most likely)
Sites Identified
  Prioritization
  Customer acceptance

## Slide 19
Example Sites
Bank of America
www.nba.com
Ernst & Young
Barnes & Noble
Disney Online
Stream
Vanstar
etc ...

## Slide 20
Vermeer Demo