1. Project:  USER

Revision history:

Name		Date		Comment

Scottlu		11/29/90	initial version

Scottlu		1/23/90	initial version

2. Milestones

2.1 Self Hosted System

USER Development platform

- Core Window manager port - window creation, destruction, painting, updating, positioning, clipping.

- Working input system - keyboard and mouse events can be directed to windows.

- Dev Platform Complete - Window manager operational on 386. Most of USER api available for use by test groups, shell group, windowed console i/o. Support for top level window user interface, mdi, dialogs, dialog controls, menus, carets, clipboard.

Stub Compiler

- 3/486 stub generation - Working 3/486 client and server stub generation. Mips comes next. Tool generates assembly directly.

- Generate c/s stubs - Client/server stubs generated for existing api. USER is now client/server.

Serialization

- SHS Serialization complete - locks around global resources. Multiple preemptive applications can execute on USER.

Keyboard & nls

- Spec unicode & language - Specify and get approval on unicode and language api support.

- SHS Keyb & nls complete - Enough keyboard support for the self-hosting workstation (all keys useable).

Input System

- Finish core input system - Finish complete input pipeline (from device drivers to application). Finish all input window message processing.

- Interprocess send/notify - Window message sending across processes and threads.

- Full hook support - support for event based hooks into USER, callable from within any context.

- Journalling - Support for mouse/key event recording and playback.

- SHS Input complete - Input pipeline, processing, assigning, queueing complete. Multiple application support for input processing and window messages complete.

Mips / Jazz support

- Mips Debug - Debug USER on Jazz system, get it working. From this moment on USER is maintained on both x386 and mips in working order.

2.2  Software Development Kit

Keyboard & nls

- Keyb table driven - Enable support for keyboard layouts (US, Great Britain, Dvorak, etc). Only provide US keyboard layout for SDK.

- SDK Keyb & nls complete - Win3.0 level functionality complete for US case only.

Security

- SDK Security complete - All access type checks are in, auditing calls are in where neessary. USER is fully security-enabled.

2.3  Product 1

Security

- Logon / WindowStation - Support for logon process, support for WindowStation object.

Desktop support

- Desktop apis - Apis for creating / managing multiple "desktops" on single display or multiple physical displays.

- SDK Desktop complete - Desktop apis complete and security-enabled.

Input System

- Full async input support - The input system fully deals with hung applications correctly - user interface, window redraw, process termination, etc.

- Hard error handling - GUI interface for display device specific messages for i/o and exception errors.

- Shutdown support - System shutdown support - close applications, shutdown file systems, etc.

- P1 Input complete - input system, window message management, inter-process message sending, hung app support all complete.

Keyboard & nls

- Intl keb layouts - Support for all international keyboard layouts that Win3.0 current supports.

- Unicode & language support - Support for all unicode and language specific apis.

- Intl sort & map tables - Support for all international string sorting orders and character case mappings.

- P1 Keyb & nls complete - All keyboard and nls support complete.

Win3.1 feature integration

- Win3.1 unspecified - this is a list of USER changes currently specified in the Win3.1 spec that need to be integrated into 32 bit USER. This spec is still evolving and features are being added weekly.

- P1 Win3.1 complete - All USER specific Win3.1 features have been integrated and debugged.

3.  Dependencies/Risks

- Win3.1 - Features are still being added to Win3.1. Feature freeze is scheduled for 12/1. It is likely to ship in summer. There is adequate time in the schedule for unknowns.

- NLS - We have not finalized the design of NLS support in USER.

- GDI - We are completely dependent on GDI for graphical output. We are completely dependent on GDI for progress on the Jazz platform.

4.  Issues

None.  (Beyond dependancies listed above.)