NTFS DEVELOPMENT PLAN AND SCHEDULE

Overview

This document details the NTFS development plan for NT 5.0 (nee Cairo) with an anticipated RTM around the middle of 1997.  The NTFS team has developed this plan to deliver some high impact features in 1997, while at the same time laying the foundation for subsequent releases.

The NTFS team understands the impact of releasing as many new important features as possible in 1997 while at the same time improving performance; however we also realize the substantial risk involved in scheduling too many new items into a single product cycle.  The plan presented here is the best compromise we have that weighs the cost of each item against its potential benefit.  By cost we mean the development, testing, and scheduling risk of the item.

The NTFS development plan for NT 5.0 has been divided into three general areas based roughly upon user visible deliverables.  These areas are

- Volume Management Features,

- Enhanced Query Features, and

- Performance Improvements.

The rest of this document considers each of the above items in detail, list of few items that we’ve specifically removed from NT 5.0, and then gives a preliminary development schedule.

Volume Management Features

The volume management features cover those items that improve the general usability of NTFS.  The scheduled features are:

- Quotas.  This is an important feature that will be ready to RTM in NT 5.0

- Cluster support.  Essentially cluster support in NTFS is enhanced code to better support dismount and volume verification and validation.  These features will be ready to RTM in NT 5.0

- Object Id support for link tracking.  The object Id support is simply a tool used by OLE to implement efficient link tracking.  We will be doing the background work to support link tracking and the item feature will be ready to RTM in NT 5.0.

- Junction point and HSM support.  We will be laying the groundwork for this support, but it probably will not be ready for NT 5.0 and will have to ship in a subsequent release.

- Improved security features.  From a user viewpoint the main security improvement is to have a separate ACL on property sets and the data stream.  This will allow an administrator to protect property sets independent of the data stream.

Enhanced Query Features

From a user perspective, NTFS will be expanded to support a richer set of queries than the dull ubiquitous directory query available today.  We will allow the user to query contents and query properties.

- Query on contents.  This is the CI work being done today, it will allow a user to query docfiles, html files, random text files,  and so forth.  Downlevel query will be available in Gibraltar in 1996 and will share common code with the query shipped in NT 5.0.  This enhanced feature will be ready to RTM in NT 5.0

- Query on properties.  Query on properties is closely tied to query on contents.  NTFS will be expanded to support native properties.  A native property is of the same form as a docfile property but by being stored natively it benefits from the file system’s meta-data transaction support, and can be indexed by the file system.  This implies that queries of native properties will always be up-to-date.

The two query enhancements mentioned above are the main new features visible to the user.  To implement these features requires putting into NTFS some general building blocks.  These building block are:

- General index support.  This is simply an extension of the file name index that exists today in NTFS.  It will allow the CI and property set code to create an index over arbitrary data.

- Native properties.  As was mentioned earlier, native properties mimic docfile property format but will be stored natively as a stream in NTFS and a user will be able to quickly query for certain properties.

- Views over native properties.  This is really an optimization required to make queries of properties tolerable.  Views will be built up using general NTFS index support.  This optimization is a lot of development work and will not be ready to RTM in NT 5.0

- File changes.  CI needs to know when files change.  The current NT design using change notification does not adequately support robust notification across reboots or system failures.  To solve this problem will require either beefing up change notification to work across reboots, or to implement simple USN support in NTFS.

Note that these building blocks are for implementing our enhanced query features, however these are the same building block needed to construct a general ISAM product in a later release.

The NTFS team expects to have query on contents and query on properties ready to RTM in NT 5.0.  Some of the code may not be fully optimized but we expect to have a usable feature set ready to ship.

Performance Improvements

Between the beta for SUR and SUR shipping NTFS will have two important performance enhancements added.  The first one is supporting large clusters and the second is a fast stat call.  Both of these features should have been added long before the beta date but development time was never available to do the work.  To avoid such a fiasco in the future the NTFS team up-front needs to have time dedicated to work on performance.  We have identified a few areas where performance can be improved.  There are plenty more areas that still need to be investigated.

- Compressed I/O.  The work for this is done, but cycles need to be committed to test, debug, and get the feature ready to ship.  This feature will be ready to RTM in NT 5.0

- Faster I/O operations.  We identified a few areas where the basic I/O operations need to be sped up, mainly create and close.  In addition, there are probably more special purpose fast I/O calls that would increase performance.  We fully expect to make more progress in this area before we RTM in NT 5.0

- Caching security checking.  This operation can be improved via a multi-phase approach.  If NTFS implements security IDs, then it can cache access checking and possibly do trimming of queries based on cached security checks.  All of this may not be ready to RTM in NT 5.0 but the work will have been started.

Features Not Currently Scheduled or Architected

There are some features that the NTFS team specifically dropped from its work list.  These features have not been architected or scheduled into the plan.  Work on these items can scheduled at a later date; however the NTFS team does not anticipate doing the work in the foreseeable future.

- Undelete

- User transactions

- Fancy replication support using timestamps on streams and ACLs

- Native Docfile implementation

- Class ID

- Copy on write streams.  As a model, COW streams simply provide the user with the ability to do a very quick copyfile operation.  From a user viewpoint once a COW is created it behaves as an ordinary file.  Transactions should be considered separate to whether a stream is a COW or not.

- General ISAM.  Though we will have some of the constructs in place for building in general ISAM support the actual item is unscheduled.

Schedule

Here is a general schedule for the key features and milestones in NTFS from the SUR Beta until NT 5.0 is code complete.  Note that in the following list the assigned SDE isn’t that important or accurately describes who is doing the work.  It is really the code complete date that is important.  Code complete means the code is checked in, developer tested, and ready for testing.

- SUR post beta performance work

- Performance Improvements

- Large cluster support (BrianAn, 2/20)

- Fast stat call (DarrylH, ?)

- NT 5.0 work

- Volume Management Features

- Quotas (JHavens, 8/23/96)

- Cluster support (Brainan, 11/1/96)

- Object Ids (Jhavens, 9/20/96)

- Format/Chkdsk Changes (GeorgeJe & MattBr, 8/16/96)

- Enhanced Query Features

- Gibraltar query (KyleP, code complete 3/15)

- General indexing support (TomM, 2/1)

- Native properties support (MarkZ, 11/22/96)

- Query on contents (KyleP, 12/13/96)

- Query on properties (Kyle & MarkZ, 2/21/97)

- Performance Improvements

- Compressed I/O (TomM, 9/23/96)

- Faster I/O operations (All, 12/30/96)

- Caching security checking (MarkZ, 12/20/96)

- Post NT 5.0 work

- Volume Management Features

- Junction points and HSM support (Who, ?)

- Improved security features (Who, ?)

- Enhanced Query Features

- View over native properties (MarkZ, ?)

- Performance Improvements

- Copy on write streams (Who, ?)